D6 · Channel launch: the first 90 days

Strata Sense is fictional; all data synthetic (MBA capstone). Economics: D6_Partner_Economics.xlsx. Strategy: D6_Channel_Strategy_Deck.pptx. Day 1 = approval of the channel plan (week 8, FY27).

# Goal for day 90

Six of FY27’s eight partner activations signed (PR01, PR02, PR06, PR07, plus P07 and P10 reactivated), PR09/PR10 pilot scope agreed, 12 engineers in certification, ₹6 cr of registered partner pipeline, and zero unresolved conflicts. No partner revenue is expected in 90 days: DR6 puts first deals at 6–12 months. The 90 days build the rules, the team and the pipeline that make FY27’s ₹3.7 cr of partner-sourced ARR possible and FY28’s ₹9.9 cr likely.

# Plan by month

| Days | Actions | Owner | Done when |
| --- | --- | --- | --- |
| 1–30: rules and people | • Publish tier terms (10% / 18% + 8% / 22% + 10% + services), deal-registration rules and conflict rules • Restrict P05 and P11 (Inject 3): letters sent, Helix-account registrations frozen, top deals moved to direct AEs with the D5 battlecard • Send exit notices to P01, P03, P04, P06, P14 • Start VP Channel search; appoint interim owner (CRO’s chief of staff) • Load 14 partners and 12 prospects into CRM; add partner-source and registration fields (fixes D1 mis-tagging) | CRO; RevOps; Legal | Terms signed off by CFO; P05/P11 acknowledge restriction; CRM fields live |
| 31–60: sign and certify | • Sign PR01 (Indonesia), PR02 (Thailand), PR06 (Singapore); term sheets to PR07 (Saudi), PR09 and PR10 (embed pilot) • Activation plans with P07 and P10: two engineers each into certification, joint list of 10 accounts • Run first certification cohort (installation and TrueSense analytics), demo kits shipped • Hire partner manager 1 (SEA) • AE comp plan updated: 50% quota credit on partner-sourced deals, counted once in bookings | Interim channel owner; Enablement; HR | 3 new partners signed; 8+ engineers enrolled; comp change communicated |
| 61–90: pipeline and review | • Joint account plans: each active partner owns 10 named low-touch or SEA accounts (from D2 tiers) • First co-sell calls with SE support on at least 6 opportunities • Sign PR07; PR09/PR10 pilot scope agreed (sensor fitted to one machine model each) • Hire partner manager 2; VP Channel offer made • First quarterly scorecard for all active partners; partner-sourced ARR added as a forecast line (D4 process) | Partner managers; SE lead; VP Channel (if hired) | ₹6 cr registered pipeline; scorecard issued; forecast line live |

# Measures we report every two weeks

| Measure | Day 30 | Day 60 | Day 90 | Why it matters |
| --- | --- | --- | --- | --- |
| Partners signed or reactivated (of 8 for FY27) | 0 | 3 | 6 | Ramp: partners activated late in FY27 add almost nothing until FY28 |
| Engineers in certification / certified | 0 / 0 | 8 / 0 | 12 / 6 | Silver needs 2 certified engineers, Gold 4 |
| Registered partner pipeline (₹ cr) | — | 2 | 6 | About 10 qualified deals per mature partner a year |
| Registration decisions within 48 hours | — | ≥ 90% | ≥ 90% | Slow approvals are the main source of conflict |
| Open conflicts older than 5 working days | 0 | 0 | 0 | Measures whether the rules are working |
| P05 / P11 registrations in Helix-incumbent accounts | 0 | 0 | 0 | Inject 3 restriction holds |

# Budget in the first 90 days

About ₹0.9 cr of the ₹3.94 cr FY27 channel budget: part-year partner manager (₹0.1 cr), recruiting fees for the VP Channel (₹0.15 cr), first certification cohort and demo kits (₹0.15 cr), PRM and CRM configuration (₹0.2 cr), and the first ₹0.3 cr of partner marketing funds, released only against signed joint plans. Channel roles stay at three in FY27, inside the limit of six, and fixed cost stays within the Inject 1 allocation of ₹2.84 cr.

# Risks and what we do

| Risk | Early sign | Response |
| --- | --- | --- |
| Helix-tied partners steer deals to Helix (Inject 3) | Registered deal switches to Helix; P05/P11 registrations in Helix accounts | Loss of tier immediately; move account to direct; review both at end-Q2 |
| SEA recruits slow to certify | Fewer than 8 engineers enrolled by day 60 | Partner manager on site; certification fees waived for first cohort |
| AEs resist partner deals | Registration disputes; AE-created duplicates on registered accounts | 50% quota credit; CRO rules on appeals; duplicate check in CRM |
| VP Channel hire delayed | No offer by day 75 | Interim owner continues; do not delay partner signings |
| Partners perform like FY26 India partners | Registered pipeline under ₹3 cr at day 90 | Stop FY27 wave-2 recruiting; kill gate at end-Q2 FY28 (fewer than 10 active or under ₹6 cr trailing partner ARR) |

# Partner by partner: status on day 90

| Partner | Decision (D6) | Day-90 target | If missed |
| --- | --- | --- | --- |
| P02 Deccan | Keep: Gold | Gold terms signed; 4 open deals registered | Coach |
| P09 Vindhya | Keep: Gold (services) | Managed-monitoring offer priced; 3 deals registered | Coach |
| P12 Siam, P13 Al Fajr | Keep: Silver | Joint plan of 10 accounts each | Move to referral |
| P05 Sahyadri, P11 Konkan | Fix: restricted (Inject 3) | Restriction acknowledged; non-Helix pipeline registered; disclosure on every deal | Exit at end-Q2 review |
| P07 Mekong, P10 Penang | Fix: activate | 2 engineers each in certification; 10-account plan | Exit at end-Q2 |
| P08 Hosur | Fix: OEM pilot | Pilot scoped alongside PR09/PR10 | Exit |
| P01, P03, P04, P06, P14 | Exit | Notices served; registrations closed | — |
| PR01, PR02, PR06 | Recruit (Q1) | Signed; certification cohort 1 | Escalate to CRO |
| PR07 | Recruit (Q2) | Signed by day 90 | Slip to Q3 |
| PR09, PR10 | Embed pilot | One machine model each agreed | Revisit in FY28 |
| PR03, PR04, PR11 | Hold for FY28 | Introductory meeting only | — |
| PR05, PR08, PR12 | Deprioritise (Helix) | No contact | — |

Decision needed on day 1: approve the tier terms, the P05/P11 restriction, the five exits, three channel roles and ₹1.5 cr of partner marketing funds from the ₹24 cr programme budget.