Memo to the CEO: the revenue reset, and what I need from the board

From the Revenue Strategy Lead · Week 9 FY27 · Strata Sense is fictional; data synthetic. Every number is from D7_Integrated_Model.xlsx.

# The recommendation

Approve ₹14.95 crore of FY27 investment (inside the ₹15 crore cap), six net new AEs starting Q3, three channel roles, and a ₹1.9 crore reserve released only if Q2 targets are met. The plan takes ARR from ₹310 crore to ₹351 crore (FY27), ₹423 crore (FY28) and ₹526 crore (FY29), ahead of the board’s ₹522 crore. It breaks even on EBITDA in FY28 (₹2.6 crore) and earns ₹52.6 crore in FY29. Doing nothing leaves us at ₹389 crore.

The trade-off I am asking you to accept: FY27 grows 13.2%, not 15% (₹5.6 crore short). Q1 was set by the pipeline on 1 April, and new AEs take a year to become productive. Buying the gap with the extra ₹3 crore does not pay back inside the CFO’s 15 months.

# Why growth stalled, in one paragraph

Win rate fell from 27% to 17% and NRR from 118% to 99% in three years. The biggest cause (₹34 crore a year) is Helix bundling our category into its automation contracts; that is a packaging problem, not a sales problem. The rest is ours to fix: AEs spent 62% of their time on accounts that produce 12% of wins, deals were single-threaded, and discounts rose without buying wins. The plan fixes these three and about a third of the Helix loss.

# What changes

- First 30 days: tiers applied to territories; discounts above 15% need the CFO; Commit means stage 5; Helix-tied partners restricted; CEO meeting with Vajra.

- By day 60: retention squad and value-selling training live; three SEA partners signed; offers out to six AEs.

- By day 90: the Q2 review decides whether the reserve is released.

- We stop: sending AEs to 1,600 low-touch accounts; matching Helix’s free offer; Commit calls before stage 5; planning on a six-month ramp; carrying dormant partners; hiring AEs to quota instead of to pipeline.

# The three largest risks

| Risk | Probability | Impact (model) | Fallback |
| --- | --- | --- | --- |
| Helix pressure deeper (churn +2 pts) | 35% | −₹23 cr FY29 ARR | Second retention squad; win-back when HelixAsset’s free period ends (Mar 2027) |
| Win-rate programme stalls (−3 pts) | 30% | −₹26 cr; payback breach at −0.7 pts | Hold reserve; move to CFO-capped path |
| Hardware share does not fall | 35% | Gross margin 64.5% by FY29 (floor 66%) | Hardware price floor; software-led expansion; sensor-agnostic tier |

# How the board will know: continue, adjust or stop at Q2

Continue if win rate ≥ 18.0%, new qualified deals ≥ 95 a quarter, H1 churn and contraction ≤ ₹13.5 crore, H1 expansion ≥ ₹12.5 crore and payback ≤ 30 months. Adjust (hold the reserve) if win rate or pipeline misses. Stop the Q3 hires and come back to the board if win rate is below 17% and payback above 32 months.

# Guardrails, and the one I am asking you to waive

Investment, gross margin, S&M ratio, headcount and the Q4 FY28 payback test are all met. One is not: Q1 FY27 CAC payback is 31.0 months against 30, because its bookings were locked before the plan. I ask for an exception for that quarter only. Q3 FY27 is tight at 29.4 months, which is why the reserve is gated.

# What I am least sure of

That hardware will fall from ₹1.48 to ₹1.05 per rupee of new and expansion ARR. If it does not, ARR still grows but gross margin breaks the floor by FY28, and the sensor-agnostic tier becomes a margin necessity. I would rather the board knew this today than discover it in FY28.